## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Yonas Getachew Dejene | Project Lead | y.dejene@alustudent.com
Brian Kiki K. Nakuwa | Project Lead | b.nakuwa@alustudent.com
Derrick Gatete | Project Lead | d.gatete@alustudent.com
Habibllah Ayodele | Project Lead | h.ayodele@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| a) Design the overall system architecture, mapping out how the data pipeline, REST API, and database layer connect and communicate. b) Write the Python-based data processing scripts responsible for ingesting the raw .parquet and .csv trip records, handling data cleaning, and engineering derived features for deeper analysis. c) Ensure that the backend services, database schema, and API contracts stay consistent across the team throughout the development process. | Yonas Dejene | 2026-02-19 | Completed | Yes | Reach out to the facilitator and ask clarification on the dataset as they appear to be missing out columns and defferent from what is mentioned on the project
| a) Collaborate with Yonas on the data processing pipeline, focusing on the cleaning logic used to detect and resolve missing values, duplicate records, and statistical outliers. b) Handle backend integration, making sure that the cleaned and feature-engineered data passed correctly through the pipeline and is formatted properly for both database insertion and API consumption by the frontend. | Brian Nakuwa | 2026-02-19 | Completed | Yes | Completed the delegated tasks
| a) Design a normalized relational schema in SQLite, defining the fact and dimension tables, foreign key relationships, and column constraints. b) Write the SQL scripts for table creation, data migration, and batch insertion of the processed trip records. | Derrick Gatete | 2026-02-19 | Completed | Yes | asses if the things implemented meet the rubrics requirement
| a) Build the interactive web dashboard using HTML, CSS, and JavaScript, integrating Chart.js to render dynamic visualizations such as time-series charts, fare distributions, and trip summaries. b) Implement filtering and sorting controls that send parameterized requests to the Flask REST API, and make sure the JSON responses are parsed and rendered correctly in real time. | Habibllah Ayodele | 2026-02-19 | Completed | Yes | check if the frontend can be intergrated with the backend
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-02-06 | Went through the Urban Mobility Data Explorer assigment, assigned tasks, and agreed on the technology stack we will use. | Derrick Gatete | Habibllah, Derrick, Brian, and Yonas | Agreed on system architecture layers and each member selected their ownership area. | Each member to set up their development environment and access the raw data files.
2026-02-09 | Reviewed progress on the data cleaning pipeline, feature engineering logic, and the SQLite schema design. | Brian Nakuwa | Derrick, Brian, Yonas, and Habibllah | Reviewed the cleaning thresholds for trip duration, trip distance, and fare amounts, as well as discussing the engineered features. | Complete the data cleaning and feature engineering.
2026-02-19 | Tested Flask API endpoints against the populated SQLite database and verified frontend API calls. | Habibllah Ayodele | Yonas, Habibllah, Brian, and Derrick | Confirmed that all REST API endpoints return correctly structured JSON responses. | Finalize everything and start writing the technical documentation report.
2026-02-22 | Verified the full system end-to-end, reviewed the technical report, rehearsed the video walkthrough, and prepared the submission package. | Yonas Dejene | Brian, Yonas, Derrick, and Habibllah | Ensured all modules run without errors and reviewed the documentation deliverables. | Submit all the deliverables.